## Instructions
INSTRUCTIONS
This estimation model is intended to be used for data integration development projects before all the detailed requirements are known. It is designed to provide an initial estimate of typical development projects, using only rough guesses of complexity and number of source systems and other interfaces, as well as the number of tables, files, and mappings involved. This estimate will need to be tuned further during the planning and scoping efforts for the project.
Estimates and weighting factors used as assumptions can be modified to adjust for initial inaccuracies, and for future sophistication and experience.
Cells where you should input information are in yellow. DO NOT change any cells that are not yellow unless you intentionally want to adjust assumptions made in this estimating model. Some cells include calculations. Do not update cells with calculations.
Step 1. "Parameters" Tab.
Fill in the IT resource daily "rates" based on resource level. End-User rates are not included here, but can be added.
Fill in the estimate for Design, Build, and Test of Informatica Mappings Based on Complexity. Default starting values have already been added.
The Design, Build, Test estimates are for resources very familiar with Informatica development. Your initial starting point may need to be higher.
Step 2. "Mapping Work" Tab.
Fill in the estimated number of source systems, and files/tables per source.
Fill in the number of Low, Medium, and High Complexity mappings to equal the total mappings calculated based on the source systems/files and tables.
See the descriptions of these categories of complexity on the Mapping Work tab.
Step 3. "WBS" tab.
Fill in the project complexity value. Override the phase level estimates, if desired.
Fill in the percentage Resource Allocation by Resource level.
Enter the process improvement charge % and risk contintengy %

## Estimating Factors
Estimating Factors
Category/Factor |  | Description
Sources
| Number | As the number of sources increases, the difficulty in building/maintaining a mapping will increase slightly
| Selection/Join criteria | Complex join criteria are tuned selection code increase the mapping development time and required tesing
| Type | Heterogeneous joins and advanced connection tools increase the complexity of the mapping. Heterogenous Joins and ERP sets specifically increase the testing difficulty. Normalized sources such as VSAM files also add to mapping complexity.
Targets
| Number | Multiple target writes in a single mapping require special attention for recovery purposes and data integrity. Creating load orders will add complexity to both development time as well as unit testing.
| Record disposition type | Using update strategies or creating mappings that do inserts or updates increase the testing difficulty as well as development.
| Target columns | Number of columns being populated within each target.
| Type | Flat file targets increase unit test difficulty.
Mapping Complexity
| Lookups | Number of lookup tables required. Complexity of lookup criteria.
| Aggregations | Number and complexity of the aggregator objects required for a mapping.
| External Transformations | TX objects significantly affect the development time as well as testing. Maintenance is also more complex.
| Stored procedures | External procedures add difficulty to mapping development as well as testing.
| Mapping objects | Overall number of objects within a mapping and the amount of dependencies between each of the objects.
Error trapping
| Complexity of checks | Complexity level of the data checkpoints within the expression object. Coding variables to calculate final error message or code adds to test and coding difficulty.
| Number of checks | Number of columns tested for errors.
| Disposition of error records | Record disposition could be to the standard bad file or to error tables. The amount of detail put into writing the records to specific admin tables could increase mapping and testing complexity.
Recovery
| Session recovery params | Coding requirements for intersession/batch control for error handling. Use of stored procedures/shell scripts as pre/post session controls for executing batches or sessions.
Reporting
| Additional Metadata | Writing records and load statistics to admin tables in parallel to target loads. Time required to complete analysis on metadata requirements, build the additional tables with appropriate keys, and code the admin table loads within the mappings. Signific
| Pre/Post session shell scripts/SQL | Post session shell scripts or stored procedures used for additional reporting capabilities. Includes parsing log files to load admin data, running stored procs to put load times into admin tables, etc. Migration from Test/QA to Prod become more difficul
| Session failure notification | Includes simple emails on completion, failures, and paging to using external shell scripts and SQL to capture reporting data and initiate communication.
Sessions/Batches
| Dependencies | Session dependencies and load orders make system testing more difficult and restart considerations more complex.
| External coding | Shell scripts and stored procedures for file manipulation, log tracking, database maintenance, etc. Migration also becomes more complex as these techniques are employed.
| Batch complexity | Nested batches increase the difficulty level for restartability and increase the system testing requirements. Also creates additional complexity to the general maintenance of the load process.
| Automation | Amount of autmation coded into the sessions for starting/re-starting loads, file transfers, initiating FTP sessions, etc.
| Scheduling | Complexity and requirements for scheduling may increase the level of difficulty in creating and maintaining mappings. System testing also more complex.
Issues
| Documentation | Availability/completeness of mapping documentation, source and target definitions, etc.
| Data availability | Source and target data sets available for unit testing during development helps identify data issues early
| Process analysis | Documented analysis of the end to end load process reduces the amount of time required for developers to complete analysis during development
WBS (Work Breakdown Structure)
The accuracy of an estimate largely depends on the experience of the estimator (or estimators). Estimates are useful for providing a close approximation of the level of effort required by the project. Factors such as project complexity, team skills, and external dependencies always have an impact on the actual effort required.
| Mapping Work Estimate | Calculations based upon complexity/number of mappings and time [Parameters] for each activity
| Complexity Estimate | Complex or broad in scope of the Project
| Project Level Estimate | Schedule for the project using the agreed-upon business project scope/complexity to determine the major tasks that need to be accomplished and estimates of the amount of effort and resources required.
| Override | Please override with actual numbers if any, from previous successful project/s

## Parameters
Spreadsheet Parameters
Staffing Parameters | Value | Detail
1 Workmonth = | 20 | Days
Project Manager | 1000 | Rate Per Day
Senior Consultant | 1000 | Rate Per Day
Analyst | 1000 | Rate Per Day
Offshore | 1000 | Rate Per Day
Mapping Complexity - design, build, test - Days | Total | Design | Build | Test | Deploy
Low | 2.63 | 0.5 | 1.5 | 0.5 | 0.13
Med | 4.33 | 0.2 | 3 | 1 | 0.13
High | 9.125 | 2 | 5 | 2 | 0.125
Maturity Factor | 1 |  | 1
Maturity of 1 is a new but well trained team with tool experience.
Use 0 for a new team that is still learning the integration platform.
Add 1 for every year of experience or for everytime volume doubles after 1st year
Maturity Adjusted Factors | Total | Design | Build | Test | Deploy
Low | 2.63 | 0.5 | 1.5 | 0.5 | 0.13
Med | 3.83 | 0.2 | 3 | 0.5 | 0.13
High | 9.125 | 2 | 5 | 2 | 0.125
Project Complexity Factors
H | 1.5
L | 0.75
M | 1
Project Phase Factors
Analyze | 0.1 | 0.3
Architect | 0.01 | 0.2
Build | 0
Deploy | 0
Design | 0
Manage | 0 | 0.2
Operate | 0
Test | 0

## Mapping Work
Low Complexity Mappings | Medium Complexity Mappings | High Complexity Mappings | Total Mappings | Mapping Build Estimate (Days)
0 | 2 |  | 2 | 7.66
Mapping COMPLEXITY - if in doubt, use the higher complexity value.
See definitions on the Estimating Factors Tab for more details on complexity considerations
LOW | Mappings with a single source (Relational or Flat-file)
Mappings which do little or no data transformation
Mappings with one or two aggregations
Mappings with no or only simple lookup transformations
Mappings with a few simple transformations, for example, data type conversions
Mappings with targets that have similar structure as the source
Mappings with straightforward loading to target (Relational or Flat-file)
MEDIUM | At least 3 of the following:
Mappings with many columns requiring data transformations
Mappings with multiple sources
Mappings with complex filtering or selection criteria
Mappings with Joins
Mappings with multiple aggregations
Mappings with complex business rules
Mappings with multiple lookups
Mappings with complex Update Strategy logic
Mappings with a first-time use of a standard connector type
Mappings with simple exception handling
Mappings with multiple targets
Mappings/Sessions with complex scheduling and dependencies
Mappings/Sessions with other batch processing complexities.
HIGH | Mappings with more than three of the factors listed under MEDIUM plus at least one of the following
Mappings with heterogenous/non-standard sources
Mappings with External Procedures, Stored Procedures, Java Calls or User Defined Functions
Mappings with a non-standard target type (XML, Application Connector, PowerExchange, etc.)
Mappings with complex exception handling
Mappings/Sessions with complex pre/post processing
Mappings with recovery procedures

## WBS
Project Estimating Model
Project Phase Estimates (numer of days) | Project Work Estimate | Override | Mapping Work Estimate | Total Work Effort Estimate | Project Manager | Senior Consultant | Analyst | Offshore | Total | Project Manager | Senior Consultant | Analyst | Offshore | Users | Notes
Manage | 0 |  |  | 0 | 100% |  |  |  | 100% | 0 | 0 | 0 | 0 | 0
Analyze | 1.149 |  |  | 1.149 |  | 25% | 75% |  | 100% | 0 | 0.28725 | 0.86175 | 0 | 0
Architect | 0.1149 |  |  | 0.1149 |  | 75% | 25% |  | 100% | 0 | 0.086175 | 0.028725 | 0 | 0
Design | 0 |  | 0.4 | 0.4 |  | 50% | 50% |  | 100% | 0 | 0.2 | 0.2 | 0 | 0
Build | 0 |  | 6 | 6 |  | 10% | 40% | 50% | 100% | 0 | 0.6 | 2.4 | 3 | 0
Test | 0 |  | 1 | 1 |  | 10% | 40% | 50% | 100% | 0 | 0.1 | 0.4 | 0.5 | 0
Deploy | 0 |  | 0.26 | 0.26 |  | 10% | 90% |  | 100% | 0 | 0.026 | 0.234 | 0 | 0
Operate | 0 |  |  | 0 |  | 10% | 90% |  | 100% | 0 | 0 | 0 | 0
Total Direct Staff Effort | 1.2639 | 0 | 7.66 | 8.9239 | [5 empty] | 0 | 1.2994 | 4.1245 | 3.5 | 0
TOTAL
Project Complexity (H, M or L) | H | [7 empty] | Direct Cost | 0 | 1299.425 | 4124.475 | 3500 | 0 | 8923.9
Process Improvement Charge | 0% | [7 empty] | With Process Improvements | 0 | 1299.425 | 4124.475 | 3500 | 0 | 8923.9
Risk Contingency | 20% | [7 empty] | With Risk Contingency | 0 | 1559.31 | 4949.37 | 4200 | 0 | 10708.68
Use a phase Override if the Complexity values do not match the expected effort.
Note that time lines can be modified in some cases by adding resources
Project COMPLEXITY
Use a best guess based on experience for selecting the Complexity value for each Phase
LOW
Project has limited scope and dependency
Project is similar to earlier successful project
Project teams are small and have worked together before
Team members are in the same departments
Application is a departmental application
There are no hardware changes
There are limited software changes
There are no technologies new to the development team
MEDIUM
Application logic or processinng involves several systems, with interdependencies
Projects involve more than one department
Project contains limited number of unfamiliar technologies or methods
Teams include members of other departments or include contractors or off-shore resources
Application has more than departmental impact
There are limited hardware configuration changes or additional hardware purchases and configuration required
There are limited software changes and/or new software
HIGH
More than two of the items under MEDIUM describe this project
Project has Enterprise level of impact
Project involves implementing new technologies or methodologies
New hardware or software is required
Diverse team: off-shore team, more than one system integrator, many departments involved
Many external linkages and dependencies
Complex business rules
Note on O3: Time spend by Client's resources